Resource 6: Sample Timeline and Timeline Template for Developing a State Plan to Ensure Equitable Access to Excellent Educators

Resource 6 provides two timelines: (1) a sample timeline to help state education leaders consider the time frames that will work in their own state context; and (2) a timeline template, in which states can indicate the major activities of their equity planning process, audience, organizer, time frame, expected results, and evidence of progress. Although the sample timeline is intended primarily for state education agencies (SEAs) as part of their technical assistance to local education agencies (LEAs), SEA staff may wish to supply a similar timeline for designing and implementing equitable access initiatives.

Note: This resource is one of 12 companion resources to the Moving Toward Equity Stakeholder Engagement Guide (http://www.gtlcenter.org/stakeholder_engagement_guide). These 12 resources are provided in a format that allows for state adaptation (e.g., Microsoft Word, PowerPoint) so that they are useable in each state’s unique context. The Center on Great Teachers and Leaders grants permission for you to use or adapt the Moving Toward Equity resources for your SEA or LEA as needed.

Sample Equitable Access Planning Timeline

| Major Activities | Parties Involved | Organizer | Time Frame | Expected Results | Evidence of Substantial Progress Made |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Start | Frequency |  |  |
| Gather and review data. | Internal SEA team | SEA | Fall 2014 | Ongoing | SEA receives, reviews, and/or adds to the data profile provided by the U.S. Department of Education (ED) and other state data. | Gaps in data may be identified at this point and spark new plans for investigation; key messages about the findings from the data are developed. |
| Identify and recruit stakeholders groups to inform the educator equity plan and build a longer term coalition to see it through. | Internal SEA team | SEA | Fall 2014 | Updated as needed | Coalition membership and stakeholder groups are identified. | Coalition members and stakeholders are broad and diverse, and they commit to assisting with this effort. |
| Prepare data materials to share with stakeholders. | Internal SEA team | SEA | Winter 2015 | One time only (updated as needed) | Discussion materials are created for diverse stakeholder groups. | Discussion materials will be created for diverse stakeholder groups. |
| Meet with stakeholders to establish short- and long-term planning goals, roles, and responsibilities. | Stakeholders | SEA | Fall 2014/ Winter 2015 | Monthly | A shared vision is established, which includes a coalition of partners committed to sustaining and monitoring the plan over 3–7 years. | By the end of this meeting series, roles, responsibilities, and timelines for the equity plan development process and long-term implementation process will be confirmed. |
| Collect and collate input from stakeholders. | Stakeholders | Stakeholders/ SEA | Winter 2015 | As needed depending on group | Stakeholders gain an understanding of the data and the SEA gains insight into on-the ground realities. | Input includes both potential priorities for the plan and insight into areas for further research. |
| Review stakeholder input, begin setting priorities, and identify metrics. | Internal SEA team and stakeholders | SEA | Winter 2015 | One time | SEA team sets priorities for the plan with stakeholder input. | SEA team will have a clear set of recommendations from stakeholders before drafting the plan. |
| SEA drafts educator equity plan. | Internal SEA team | SEA | Winter 2015 | One time | An equitable access plan that includes contributions from a wide set of stakeholders. | Stakeholders have a concrete plan to react to and provide feedback. |
| Present plan draft to stakeholders, collect comments, and revise. | Stakeholders | Stakeholders/ SEA | Winter/ Spring 2015 | Multiple meetings as needed | Revisions to and comments about the plan are provided by stakeholders. | Stakeholders recognize their contributions in the structure and content of the draft. |
| Finalize plan. | SEA and ED | SEA | Spring 2015 | One time | Plan is submitted by April 2015. | SEA meets requirements of ED. |
| Implement plan. Conduct ongoing monitoring and continuous improvement of the plan | Long-term coalition of stakeholders | SEA and stakeholders | Summer 2015 | Ongoing, indefinitely | Implementation is smooth, and ongoing adjustments strengthen the design and implementation of the plan. | All students have equitable access to excellent teaching and leading in their schools |

Equitable Access Planning Timeline Template

| Major Activities | Parties Involved | Organizer | Time Frame | Expected Results | Evidence of Substantial Progress Made |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Start | Frequency |  |  |